## Slide 1
Weekly Status Report : 13 Apr - 17 Apr, 2026
1. Project Status
Development | PO Awaited | UAT | Go Live | In UD | On Hold | UD Not Started | Grand Total
0 | 2 | 5 | 2 | 4 | 0 | 0 | 15

## Slide 2
2. Project Aging Summary
index | 0 - 30 Days | 30 - 60 Days | 60 - 90 Days | > 90 Days | UD Not Started | Grand Total
Dev | 0 | 0 | 0 | 0 | 0 | 0
PO Awaited | 2 | 0 | 0 | 0 | 0 | 2
UAT | 1 | 1 | 1 | 2 | 0 | 5
In UD | 7 | 1 | 0 | 0 | 0 | 8
On Hold | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 10 | 2 | 1 | 2 | 0 | 15
3. Delivery Highlights
Message
No deliveries in last 7 days

## Slide 3
4. Risks / Aging Projects
Project Module | Status Code | Aging From Date | Aging (Days)
Enabling UPI on CRM Funding Link for customers - InstaFund | UAT | 08-May-2025 | 349
PIS Account ENET Form Changes | UAT | 05-Jan-2026 | 107
ISA ¦ NDML circular on usage of KRA by MFD | UAT | 09-Feb-2026 | 72
5. Executive Summary
• Here are 5 executive weekly status bullets:
• Our portfolio currently manages 15 active projects, with 2 successfully delivered and 5 in UAT.
• A key project successfully went live on April 13th, contributing to our delivered count.
• Five projects are in UAT, with two facing external dependencies related to API prerequisites and UIDAI issues.
• Three projects remain delayed beyond 60 days, and we are actively addressing their respective blockers.