## Raw Data
Project Module | Module ID | Status Code | Actual FSD Delivery | Actual FSD Sign Off | Actual Dev Delivery Start | Actual Dev Delivery End | Actual UAT Start | Actual UAT Sign Off | Actual Go Live | Description
Authentication Type Stamping in AOF | 119003 | UAT | 31-03-2026 | 02-04-2026 | 06-04-2026 | 07-04-2026 | 09-04-2026 |  |  | 16-04-26: UAT Delivery done, Awaiting sign off 09-04-26: UAT Delivery planned for today 02-04-26: UD sign off. 31-03-26: UD submitted. Awaiting sign off. 26-03:26: RD received.
Business Debit Card ¦ SSO Integration with Line6 | 118647 | UD submitted | 05-01-2026 | [6 empty] | 16-04-26: No updates from Bank on the status. 02-04-26: Mehul to check and confirm on the status. 26-02-26: Awaiting UD signoff 18-02-26: Awaiting UD signoff 05-02-26: Awaiting UD signoff 22-01-26: Awaiting UD sign off 18-12-25: RD Received
Private Banking questionnaire changes in journey and PDF | 118686 | Pre - Engagement | [7 empty] | 05-02-26: Awaiting updated RD 29-01-26: Awaiting updated RD 22-01-26: Awaiting updated RD 26-12-2025: RD Received on 22 Dec
PIS Account ENET Form Changes | 118576 | UAT | 27-11-2025 | 28-11-2025 | 15-12-2025 | 18-12-2025 | 05-01-2026 |  |  | 09-04-26: UAT testing in progress. Awaiting UAT sign off. 26-02-26: UAT testing in progress. Tentative MTP plan in March 18-02-26: Awaiting UAT sign off. Tentative MTP plan in March 05-02-26: UAT testing in progress. Tentative MTP plan in March 22-01-26: UAT testing in progress. Tentative MTP plan in March 08-01-26: UAT in progress 11-12-25: PO will be shared by next week. 27-11-25: UD to be delivered by tomorrow.
New Form Creation - Form 97 | 119071 | UD submitted | 20-04-2026 | [6 empty] | 16-04-26: UD to be shared by early next week. 10-04-26: RD Received
CRM NRI AOF ¦¦ New Form Version Implementation | 119072 | Pre - Engagement | [7 empty] | 10-04-26: RD Received
Disableling Debit auth in SSS journeys. | 119073 | UD signed off | 13-04-2026 | 17-04-2026 | [5 empty] | 16-04-26: Awaiting signoff 13-04-26: RD received and UD submitted
Migration of DAP Microservice to Cloud | 119074 | UD submitted | 26-03-2026 | [6 empty] | 16-04-26: Awaiting signoff from technical side. Functional sign off received. 09-04-26: Awaiting UD signoff. 26-03-26: UD submitted 18-03-26: RD Received
Addition of columns in Liabilities report | 119004 | Production Cutover | 27-03-2026 | 01-04-2026 | 02-04-2026 | 03-04-2026 | 09-04-2026 | 13-04-2026 | 13-04-2026 | 16-04-26: MTP done on 13 Apr 26 09-04-26: UAT Delivery planned for today 02-04-26: UD signed off. Proposal to be shared. 27-03-26: UD submitted. 25-03-26: RD received.
Enabling UPI on CRM Funding Link for customers - InstaFund | 116369 | UAT | 29-01-2025 | 03-02-2025 | 17-03-2025 | 21-04-2025 | 08-05-2025 |  |  | 16-04-26: Awaiting Signoff. Prerequisites for API should be ready before production movement 09-04-26: Expected signoff by next week. 02-04-26: Product sign off awaiting. Awaiting UAT sign off. Prerequisites for api should be ready before prod movement. 19-03-26: Journey working end to end. Awaiting UAT sign off 12-03-26: Issue raised for transaction API. Need to check and confirm 05-03-26: Sudarshan to check and update. 26-02-26: Journey working end to end. BTG to release for testing. 18-02-26: Patch to be shared by tomorrow. 29-01-26: Patch to be shared for raised observation. 22-01-26: Issue raised. CRM to check and share the fix. 08-01-26: Abhishek to resume UAT by tomorrow. 18-12-25: Abhishek to confirm on the Project status 11-12-25: Bank team to schedule a call for the same. 04-12-25: Awaiting update from UPI team. ETA to be shared by bank team. 20-11-25 to 27-11-25: Awaiting update from UPI team. ETA to be shared by bank team. 13-11-25: Call Setup at 4:30 for joint testing 06-11-25: Sudarshan to share for UAT testing. 30-10-25: Fixes shared. UAT Signoff to be shared by mid November. 25-09-25: Patch shared and Logs to be shared with UPI team. 04-09-25: Request to be shared with Sudarshan. 17-07-25: UAT testing in process 10-07-25: Updated Patch to be shared. 03-07-25: Revised Patch need to be shared - CRM 19-06-25: Port Opening in pending. 29-05-25: URL whitelisting still pending. 14-05-25: updated patch to be shared. 07-05-25: UAT deployment in progress 19-03-25 to 16-04-25: UAT Delivery planned for 8th May 12-03-25: PO will be shared by next week 12-02-25 to 05-03-25: FPN to be raised. 05-02-25: Proposal shared. PO Awaited 29-01-25: Awaiting UD signoff 22-01-25: UD to be shared by Friday 15-01-25: Discussion done
ISA ¦ NDML circular on usage of KRA by MFD | 118188 | UAT | 28-08-2025 | 13-11-2025 | 08-12-2025 | 30-01-2026 | 09-02-2026 |  |  | 16-04-26: Awaiting UAT Signoff 09-04-26: Expecting signoff by 13th April. 02-04-26: Awaiting UAT sign off. Tentative sign off by next mid-week. Prerequisites for API should be ready before prod movement 19-03-26: Journey running, Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25: Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress.
CRM : NTB NR Account Opening for Adobe / Smart App journey | 117374 | UD submitted | 24-07-2025 | [6 empty] | 16-04-26: FTS Confirmation and update from IDEA awaited. 09-04-26: FTS Confirmation Awaited. Awaiting update from IDEA. 26-02-26: FTS Confirmation will be shared by 12th March. Awaiting update from IDEA. 18-02-26: FTS Confirmation Awaited. Awaiting update from IDEA. 05-02-26: FTS technical document shared. Awaiting Update from IDEA. 29-01-26: IDEA and FTS details confirmation awaited. 22-01-26: IDEA and FTS details confirmation awaited. 08-01-26: IDEA and FTS call awaiting. 18-12-25: FTS call setup for 4:00 today 11-12-25: CRM mapping sheet to be shared by today 27-11-25: UD and API specs pending 20-11-25: Call scheduled for Monday 24th November 13-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 06-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 30-10-25: Callback to be taken up as seperate Project. Call to be setup with bank team for FTS KAFKA. 25-09-25: CallBack details Shared by Bank. Awaiting DMS Api Specs and call with FTS team 18-09-25: PO to be released by next week. 04-09-25: Updated FieldList to be shared by Krina. FTS Call to be scheduled to with tuesday. 24-07-25: UD submit. Awaiting UD sign off 17-07-25: UD to be shared 03-07-25: UD timeline to be shared by CRM 19-06-25: UD in progress 29-05-25: Flow discussion to be done with Abhishek. 14-05-25: Awaiting inputs.
Sending the KYC Flags for REKYC Dates Stamping to IDEA | 118692 | Production Cutover | 05-01-2026 | 06-01-2026 | 10-02-2026 | 16-02-2026 | 25-02-2026 | 01-04-2026 | 13-04-2026 | 16-04-26: Project gone live on 13 Apr 26 09-04-26: MTP planned for 13 Apr 26 01-04-26: UAT signed off 19-03-26: Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25 : Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress. 26-02-26: UAT delivery done. Deployment to be completed. 05-02-26: PO to be released by Next week Monday 29-01-26: FPN approval. PO Awaited 22-01-26: FPN approval. PO to be released by 30 JAN 08-01-26: Awaiting PO 18-12-25 : RD Received
Restriction Document Editing in CRM | 118408 | UD signed off | 09-02-2026 | 23-02-2026 |  |  | 15-04-2026 |  |  | 16-04-26: Proposal shared. Awaiting PO 09-04-26: Proposal shared. Awaiting PO 26-02-26: UD signed off. Proposal shared. Awaiting PO 18-02-26: Awaiting UD sign off 05-02-26: UD to be shared by 9th Feb. 29-01-26: UD to be shared by next week. 08-01-26: CRM to confirm on the feasibility. 11-12-25: CRM to confirm feasibility by 12th. 27-11-25: CRM will check feasibility and confirm by next week 20-11-25: Updated UD to be shared after feasibility check. CRM to confirm by next week 06-11-25: UD shared. 30-10-25: UD to be shared by next week Tuesday
Changes in Aadhaar e-KYC Response (PDF & XML) for Foreigners | 118273 | UAT | 23-07-2025 | 07-10-2025 | 02-03-2026 | 06-03-2026 | 10-03-2026 |  |  | 16-04-26: Issue at UIDAI for new response tag and test data. Awaiting ETA for UAT sign off. 09-04-26: Awaiting UAT sign off. Issue at UIDAI for new response tag and test data 02-04-26: Awaiting UAT sign off. Tentative: Next week 19-03-26: Awaiting UAT sign off. 12-03-26: UAT delivery done. Deployment and SIT in progress 26-02-26: PO Received. UAT delivery on 10th March. 18-02-26: PO Awaited. 05-02-26: PO Awaited. 29-01-26: PO Awaited 22-01-26: PO Awaited 08-01-26: PO Awaited 18-12-25: Awaiting UD signoff. UD to be signed off by 19th Dec. 11-12-25: Updated UD to be shared by tomorrow. 04-12-25: UD will be updated post receiving updated data from HDFC. 27-11-25: On hold till further confirmation from Mehul 30-10-25 to 20-11-25: PO Awaited 25-09-25: UD signoff to be shared tomorrow. 18-09-25: Manvi to connect with Sandeep and close UD 24-07-25: UD submitted. Awaiting sign off 03-07-25: Pending points confirmation from bank

## Final Data
Project Module | Module ID | Status Code | Actual FSD Delivery | Actual FSD Sign Off | Actual Dev Delivery Start | Actual Dev Delivery End | Actual UAT Start | Actual UAT Sign Off | Actual Go Live | Description | Aging From Date | Aging
Authentication Type Stamping in AOF | 119003 | UAT | 31-03-2026 | 02-04-2026 | 06-04-2026 | 07-04-2026 | 09-04-2026 |  |  | 16-04-26: UAT Delivery done, Awaiting sign off 09-04-26: UAT Delivery planned for today 02-04-26: UD sign off. 31-03-26: UD submitted. Awaiting sign off. 26-03:26: RD received. | 2026-04-09 | 13
Business Debit Card ¦ SSO Integration with Line6 | 118647 | UD submitted | 05-01-2026 | [6 empty] | 16-04-26: No updates from Bank on the status. 02-04-26: Mehul to check and confirm on the status. 26-02-26: Awaiting UD signoff 18-02-26: Awaiting UD signoff 05-02-26: Awaiting UD signoff 22-01-26: Awaiting UD sign off 18-12-25: RD Received |  | 0
Private Banking questionnaire changes in journey and PDF | 118686 | Pre - Engagement | [7 empty] | 05-02-26: Awaiting updated RD 29-01-26: Awaiting updated RD 22-01-26: Awaiting updated RD 26-12-2025: RD Received on 22 Dec |  | 0
PIS Account ENET Form Changes | 118576 | UAT | 27-11-2025 | 28-11-2025 | 15-12-2025 | 18-12-2025 | 05-01-2026 |  |  | 09-04-26: UAT testing in progress. Awaiting UAT sign off. 26-02-26: UAT testing in progress. Tentative MTP plan in March 18-02-26: Awaiting UAT sign off. Tentative MTP plan in March 05-02-26: UAT testing in progress. Tentative MTP plan in March 22-01-26: UAT testing in progress. Tentative MTP plan in March 08-01-26: UAT in progress 11-12-25: PO will be shared by next week. 27-11-25: UD to be delivered by tomorrow. | 2026-01-05 | 107
New Form Creation - Form 97 | 119071 | UD submitted | 20-04-2026 | [6 empty] | 16-04-26: UD to be shared by early next week. 10-04-26: RD Received |  | 0
CRM NRI AOF ¦¦ New Form Version Implementation | 119072 | Pre - Engagement | [7 empty] | 10-04-26: RD Received |  | 0
Disableling Debit auth in SSS journeys. | 119073 | UD signed off | 13-04-2026 | 17-04-2026 | [5 empty] | 16-04-26: Awaiting signoff 13-04-26: RD received and UD submitted |  | 0
Migration of DAP Microservice to Cloud | 119074 | UD submitted | 26-03-2026 | [6 empty] | 16-04-26: Awaiting signoff from technical side. Functional sign off received. 09-04-26: Awaiting UD signoff. 26-03-26: UD submitted 18-03-26: RD Received |  | 0
Addition of columns in Liabilities report | 119004 | Production Cutover | 27-03-2026 | 01-04-2026 | 02-04-2026 | 03-04-2026 | 09-04-2026 | 13-04-2026 | 13-04-2026 | 16-04-26: MTP done on 13 Apr 26 09-04-26: UAT Delivery planned for today 02-04-26: UD signed off. Proposal to be shared. 27-03-26: UD submitted. 25-03-26: RD received. | 2026-04-09 | 13
Enabling UPI on CRM Funding Link for customers - InstaFund | 116369 | UAT | 29-01-2025 | 03-02-2025 | 17-03-2025 | 21-04-2025 | 08-05-2025 |  |  | 16-04-26: Awaiting Signoff. Prerequisites for API should be ready before production movement 09-04-26: Expected signoff by next week. 02-04-26: Product sign off awaiting. Awaiting UAT sign off. Prerequisites for api should be ready before prod movement. 19-03-26: Journey working end to end. Awaiting UAT sign off 12-03-26: Issue raised for transaction API. Need to check and confirm 05-03-26: Sudarshan to check and update. 26-02-26: Journey working end to end. BTG to release for testing. 18-02-26: Patch to be shared by tomorrow. 29-01-26: Patch to be shared for raised observation. 22-01-26: Issue raised. CRM to check and share the fix. 08-01-26: Abhishek to resume UAT by tomorrow. 18-12-25: Abhishek to confirm on the Project status 11-12-25: Bank team to schedule a call for the same. 04-12-25: Awaiting update from UPI team. ETA to be shared by bank team. 20-11-25 to 27-11-25: Awaiting update from UPI team. ETA to be shared by bank team. 13-11-25: Call Setup at 4:30 for joint testing 06-11-25: Sudarshan to share for UAT testing. 30-10-25: Fixes shared. UAT Signoff to be shared by mid November. 25-09-25: Patch shared and Logs to be shared with UPI team. 04-09-25: Request to be shared with Sudarshan. 17-07-25: UAT testing in process 10-07-25: Updated Patch to be shared. 03-07-25: Revised Patch need to be shared - CRM 19-06-25: Port Opening in pending. 29-05-25: URL whitelisting still pending. 14-05-25: updated patch to be shared. 07-05-25: UAT deployment in progress 19-03-25 to 16-04-25: UAT Delivery planned for 8th May 12-03-25: PO will be shared by next week 12-02-25 to 05-03-25: FPN to be raised. 05-02-25: Proposal shared. PO Awaited 29-01-25: Awaiting UD signoff 22-01-25: UD to be shared by Friday 15-01-25: Discussion done | 2025-05-08 | 349
ISA ¦ NDML circular on usage of KRA by MFD | 118188 | UAT | 28-08-2025 | 13-11-2025 | 08-12-2025 | 30-01-2026 | 09-02-2026 |  |  | 16-04-26: Awaiting UAT Signoff 09-04-26: Expecting signoff by 13th April. 02-04-26: Awaiting UAT sign off. Tentative sign off by next mid-week. Prerequisites for API should be ready before prod movement 19-03-26: Journey running, Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25: Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress. | 2026-02-09 | 72
CRM : NTB NR Account Opening for Adobe / Smart App journey | 117374 | UD submitted | 24-07-2025 | [6 empty] | 16-04-26: FTS Confirmation and update from IDEA awaited. 09-04-26: FTS Confirmation Awaited. Awaiting update from IDEA. 26-02-26: FTS Confirmation will be shared by 12th March. Awaiting update from IDEA. 18-02-26: FTS Confirmation Awaited. Awaiting update from IDEA. 05-02-26: FTS technical document shared. Awaiting Update from IDEA. 29-01-26: IDEA and FTS details confirmation awaited. 22-01-26: IDEA and FTS details confirmation awaited. 08-01-26: IDEA and FTS call awaiting. 18-12-25: FTS call setup for 4:00 today 11-12-25: CRM mapping sheet to be shared by today 27-11-25: UD and API specs pending 20-11-25: Call scheduled for Monday 24th November 13-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 06-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 30-10-25: Callback to be taken up as seperate Project. Call to be setup with bank team for FTS KAFKA. 25-09-25: CallBack details Shared by Bank. Awaiting DMS Api Specs and call with FTS team 18-09-25: PO to be released by next week. 04-09-25: Updated FieldList to be shared by Krina. FTS Call to be scheduled to with tuesday. 24-07-25: UD submit. Awaiting UD sign off 17-07-25: UD to be shared 03-07-25: UD timeline to be shared by CRM 19-06-25: UD in progress 29-05-25: Flow discussion to be done with Abhishek. 14-05-25: Awaiting inputs. |  | 0
Sending the KYC Flags for REKYC Dates Stamping to IDEA | 118692 | Production Cutover | 05-01-2026 | 06-01-2026 | 10-02-2026 | 16-02-2026 | 25-02-2026 | 01-04-2026 | 13-04-2026 | 16-04-26: Project gone live on 13 Apr 26 09-04-26: MTP planned for 13 Apr 26 01-04-26: UAT signed off 19-03-26: Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25 : Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress. 26-02-26: UAT delivery done. Deployment to be completed. 05-02-26: PO to be released by Next week Monday 29-01-26: FPN approval. PO Awaited 22-01-26: FPN approval. PO to be released by 30 JAN 08-01-26: Awaiting PO 18-12-25 : RD Received | 2026-02-25 | 56
Restriction Document Editing in CRM | 118408 | UD signed off | 09-02-2026 | 23-02-2026 |  |  | 15-04-2026 |  |  | 16-04-26: Proposal shared. Awaiting PO 09-04-26: Proposal shared. Awaiting PO 26-02-26: UD signed off. Proposal shared. Awaiting PO 18-02-26: Awaiting UD sign off 05-02-26: UD to be shared by 9th Feb. 29-01-26: UD to be shared by next week. 08-01-26: CRM to confirm on the feasibility. 11-12-25: CRM to confirm feasibility by 12th. 27-11-25: CRM will check feasibility and confirm by next week 20-11-25: Updated UD to be shared after feasibility check. CRM to confirm by next week 06-11-25: UD shared. 30-10-25: UD to be shared by next week Tuesday | 2026-04-15 | 7
Changes in Aadhaar e-KYC Response (PDF & XML) for Foreigners | 118273 | UAT | 23-07-2025 | 07-10-2025 | 02-03-2026 | 06-03-2026 | 10-03-2026 |  |  | 16-04-26: Issue at UIDAI for new response tag and test data. Awaiting ETA for UAT sign off. 09-04-26: Awaiting UAT sign off. Issue at UIDAI for new response tag and test data 02-04-26: Awaiting UAT sign off. Tentative: Next week 19-03-26: Awaiting UAT sign off. 12-03-26: UAT delivery done. Deployment and SIT in progress 26-02-26: PO Received. UAT delivery on 10th March. 18-02-26: PO Awaited. 05-02-26: PO Awaited. 29-01-26: PO Awaited 22-01-26: PO Awaited 08-01-26: PO Awaited 18-12-25: Awaiting UD signoff. UD to be signed off by 19th Dec. 11-12-25: Updated UD to be shared by tomorrow. 04-12-25: UD will be updated post receiving updated data from HDFC. 27-11-25: On hold till further confirmation from Mehul 30-10-25 to 20-11-25: PO Awaited 25-09-25: UD signoff to be shared tomorrow. 18-09-25: Manvi to connect with Sandeep and close UD 24-07-25: UD submitted. Awaiting sign off 03-07-25: Pending points confirmation from bank | 2026-03-10 | 43

## Project Status
Status | Count
Development | 0
PO Awaited | 2
UAT | 5
Go Live | 2
In UD | 4
On Hold | 0
UD Not Started | 0
Grand Total | 15

## Project Aging Summary
index | 0 - 30 Days | 30 - 60 Days | 60 - 90 Days | > 90 Days | UD Not Started | Grand Total
Dev | 0 | 0 | 0 | 0 | 0 | 0
PO Awaited | 2 | 0 | 0 | 0 | 0 | 2
UAT | 1 | 1 | 1 | 2 | 0 | 5
In UD | 7 | 1 | 0 | 0 | 0 | 8
On Hold | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 10 | 2 | 1 | 2 | 0 | 15

## Delivery Highlights
Project Module | UAT / Go Live Date | Status Code

## Risks
Project Module | Status Code | Aging From Date | Aging (Days)
Enabling UPI on CRM Funding Link for customers - InstaFund | UAT | 08-May-2025 | 349
PIS Account ENET Form Changes | UAT | 05-Jan-2026 | 107
ISA ¦ NDML circular on usage of KRA by MFD | UAT | 09-Feb-2026 | 72