## Summary
Category | Count
Go Live | 2
PO Awaited | 2
UAT | 5
Development | 0
In UD | 4
On Hold | 0
Total | 15

## Project Aging Summary
| 0-30 | 31-60 | 61-90 | 91-180 | 181-365 | 365+ | Total
Pre - Engagement | 2 | 0 | 0 | 0 | 0 | 0 | 2
Production Cutover | 1 | 1 | 0 | 0 | 0 | 0 | 2
UAT | 1 | 1 | 1 | 1 | 1 | 0 | 5
UD signed off | 2 | 0 | 0 | 0 | 0 | 0 | 2
UD submitted | 4 | 0 | 0 | 0 | 0 | 0 | 4
Grand Total | 10 | 2 | 1 | 1 | 1 | 0 | 15

## Delivery Highlights
Project | Module | Status | Date
Restriction Document Editing in CRM | 118408 | UD signed off | 15-Apr-2026

## Risks
Project | Module | Status | Aging
Enabling UPI on CRM Funding Link for customers - InstaFund | 116369 | UAT | 349
PIS Account ENET Form Changes | 118576 | UAT | 107
ISA ¦ NDML circular on usage of KRA by MFD | 118188 | UAT | 72

## Executive Summary
Executive Summary
Portfolio delivery momentum maintained during the week.
Key UAT activities continue across priority programs.
Focused action required on aging items beyond 60 days.
Recent deliveries support planned business milestones.
Overall execution remains stable.