## Final Data
Customer CR No. | Project Module | Module ID | Project Name | Status Code | Applicable To | Assign To Name | Drop | RAG | CR | Effort in ManMonths | Actual FSD Delivery | Actual FSD Sign Off | Actual WUD Delivery | WUD Sign Off | Actual Dev Delivery Start | Actual Dev Delivery End | Pre SIT Start Date | SIT Start Date | Actual SIT Start | PreUAT Demo | Planned UAT | Actual UAT Start | Actual UAT Sign Off | Planned Go Live | Actual Go Live | Created On | Actual SA Start | Actual SA End | Dependency | SDG Efforts in ManMo | SAG Efforts in ManMo | ESG Efforts in ManMo | SAG Resource Name | ESG Resource Name | SDG Efforts Name | Total % Completion | Requirement Raised Date | OEG Handover Date | OEG Handover Status | Approved Efforts | PO No. | Invoice No. | Invoice Date | Finanace Status | RAG.1 | Status | Description | ESG Resource | SAG Resource | SDG Resource | Actual SIT End Date | Aging From Date | Aging
| PIS Account ENET Form Changes | 118576 | HDFC DAP PO ¦ SA ¦ PIS Account ENET Form Changes | UAT | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 1 | 27-Nov-2025 | 28-11-2025 | 27-Nov-2025 |  | 15-Dec-2025 | 18-Dec-2025 | 25-Dec-2025 | 25-Dec-2025 | 25-Dec-2025 |  |  | 05-Jan-2026 |  |  |  | 26-Nov-2025 | 26-Dec-2025 | 31-Dec-2025 |  | 0 | 0 | 0 |  |  |  | 0.00 % |  |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: UAT testing in progress. Awaiting UAT sign off. 09-04-26: UAT testing in progress. Awaiting UAT sign off. 26-02-26: UAT testing in progress. Tentative MTP plan in March 18-02-26: Awaiting UAT sign off. Tentative MTP plan in March 05-02-26: UAT testing in progress. Tentative MTP plan in March 22-01-26: UAT testing in progress. Tentative MTP plan in March 08-01-26: UAT in progress 11-12-25: PO will be shared by next week. 27-11-25: UD to be delivered by tomorrow. | Krina Shah | Tejas Baban Jadhav | Shakeel Ahmad Khan |  | 05-Jan-2026 | 119
| Digital Token - Loan Cancellation | 119267 | HDFC DAP PO 2026-2027 | Pre - Engagement | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 2 | [6 empty] | 15-Jul-2026 | 15-Jul-2026 | 15-Jul-2026 |  |  | 15-Jul-2026 |  |  |  | 04-May-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 20-Apr-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: Updated final RD with details awaited. Tentative ETA Monday 04 May 26 23-04-26: Updated final RD with details awaited 20-04-26: First draft of RD Received | Krina Shah |  |  |  | 15-Jul-2026 | 0
| Digital Token - Email id Population Logic Change | 119268 | HDFC DAP PO 2026-2027 | Pre - Engagement | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 2 | [6 empty] | 15-Jul-2026 | 15-Jul-2026 | 15-Jul-2026 |  |  | 15-Jul-2026 |  |  |  | 04-May-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % |  |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: RD received. | Krina Shah |  |  |  | 15-Jul-2026 | 0
| Digital Token - Textual change for change in EMI repayment | 119269 | HDFC DAP PO 2026-2027 | Pre - Engagement | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 0.2 | [6 empty] | 15-May-2026 | 15-May-2026 | 15-May-2026 |  |  | 15-May-2026 |  |  |  | 04-May-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 30-Apr-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: RD awaited with all details. | Rachael Lobo |  |  |  | 15-May-2026 | 0
| Business Debit Card ¦ SSO Integration with Line6 | 118647 | HDFC DAP PO¦ Business Debit Card ¦ SSO Integration with Line6 | UD submitted | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 2 | 05-Jan-2026 | [5 empty] | 18-Feb-2026 | 18-Feb-2026 | 18-Feb-2026 |  |  | 18-Feb-2026 |  |  |  | 19-Dec-2025 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 18-Dec-2025 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 30-04-26: Functional sign off received. Final sign off by next week. 16-04-26: No updates from Bank on the status. 02-04-26: Mehul to check and confirm on the status. 26-02-26: Awaiting UD signoff 18-02-26: Awaiting UD signoff 05-02-26: Awaiting UD signoff 22-01-26: Awaiting UD sign off 18-12-25: RD Received |  |  |  |  | 05-Jan-2026 | 119
| Private Banking questionnaire changes in journey and PDF | 118686 | HDFC DAP PO ¦ Private Banking ¦ Questionnaire change - RBI Mandate | Pre - Engagement | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 2 | [6 empty] | 10-Mar-2026 | 10-Mar-2026 | 10-Mar-2026 |  |  | 10-Mar-2026 |  |  |  | 02-Jan-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 22-Dec-2025 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: RD to be shared by 5 May 16-04-26: Awaiting updated RD. Shubham to share update by tomorrow. 09-04-26: updated RD to be shared by 10th April. 05-02-26: Awaiting updated RD 29-01-26: Awaiting updated RD 22-01-26: Awaiting updated RD 26-12-2025: RD Received on 22 Dec | Krina Shah |  |  |  | 10-Mar-2026 | 55
| New Form Creation - Form 97 | 119071 | HDFC DAP PO 2026-2027 | UD signed off | CRMNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 1 | 20-Apr-2026 | 21-04-2026 |  |  |  |  | 15-Jun-2026 | 15-Jun-2026 | 15-Jun-2026 |  |  | 15-Jun-2026 |  |  |  | 13-Apr-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 10-Apr-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 23-04-26: UD signed off. Proposal shared. 16-04-26: UD to be shared by early next week. 10-04-26: RD Received |  |  |  |  | 20-Apr-2026 | 14
| CRM NRI AOF ¦¦ New Form Version Implementation | 119072 | HDFC DAP PO 2026-2027 | Pre - Engagement | CRMNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 1 | [6 empty] | 15-Jun-2026 | 15-Jun-2026 | 15-Jun-2026 |  |  | 15-Jun-2026 |  |  |  | 13-Apr-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 10-Apr-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 10-04-26: RD Received |  |  |  |  | 15-Jun-2026 | 0
| Disableling Debit auth in SSS journeys. | 119073 | HDFC DAP PO 2026-2027 | UD signed off | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 0.2 | 13-Apr-2026 | 17-04-2026 |  |  |  |  | 20-Apr-2026 | 20-Apr-2026 | 20-Apr-2026 |  |  | 20-Apr-2026 |  |  |  | 13-Apr-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 13-Apr-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 23-04-26: UD signed off. Proposal shared. Awaiting PO. 16-04-26: Awaiting signoff 13-04-26: RD received and UD submitted |  |  |  |  | 13-Apr-2026 | 21
| Migration of DAP Microservice to Cloud | 119074 | HDFC DAP PO 2026-2027 | Dropped | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 1 | 26-Mar-2026 | [5 empty] | 15-Jun-2026 | 15-Jun-2026 | 15-Jun-2026 |  |  | 15-Jun-2026 |  |  |  | 13-Apr-2026 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 18-Mar-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 30-04-26: Need to be dropped. As per confirmation received from Mehul and Brijesh 23-04-26: Awaiting signoff from technical side. Keeping on hold till further confirmation 16-04-26: Awaiting signoff from technical side. Functional sign off received. 09-04-26: Awaiting UD signoff. 26-03-26: UD submitted 18-03-26: RD Received |  |  |  |  | 26-Mar-2026 | 39
| Addition of columns in Liabilities report | 119004 | HDFC DAP PO 2026-2027 | Production Cutover | CRMNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 0.2 | 27-Mar-2026 | 01-04-2026 |  |  | 02-Apr-2026 | 03-Apr-2026 | 15-Apr-2026 | 15-Apr-2026 | 09-Apr-2026 |  |  | 09-Apr-2026 | 13-Apr-2026 |  | 13-Apr-2026 | 06-Apr-2026 | 06-Apr-2026 | 06-Apr-2026 |  | 0 | 0 | 0 | Sumit | Krina |  | 0.00 % | 25-Mar-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 16-04-26: MTP done on 13 Apr 26 09-04-26: UAT Delivery planned for today 02-04-26: UD signed off. Proposal to be shared. 27-03-26: UD submitted. 25-03-26: RD received. | Rachael Lobo | Sumit Patil | Shakeel Ahmad Khan |  | 13-Apr-2026 | 21
| Enabling UPI on CRM Funding Link for customers - InstaFund | 116369 | HDFC DAP PO¦ InstaFund ¦ Enabling UPI on CRM Funding Link for customers | UAT | CustomerNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 2 | 29-Jan-2025 | 03-02-2025 |  |  | 17-Mar-2025 | 21-Apr-2025 | 15-May-2025 | 15-May-2025 | 06-May-2025 |  |  | 08-May-2025 |  |  |  | 10-Jan-2025 | 22-Apr-2025 | 02-May-2025 |  | 0 | 0 | 0 |  |  |  | 0.00 % | 08-Jan-2025 |  |  | 0 | PO/IT/ACIDAES S/00192856/2024-25 |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rcpqqx74lu5qscrq6d4xllrp72a" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: UAT still not completed and sign off awaited. 23-04-26: Still no update on UAT sign off. Project scheduled for on Hold. 16-04-26: Awaiting Signoff. Prerequisites for API should be ready before production movement 09-04-26: Expected signoff by next week. 02-04-26: Product sign off awaiting. Awaiting UAT sign off. Prerequisites for api should be ready before prod movement. 19-03-26: Journey working end to end. Awaiting UAT sign off 12-03-26: Issue raised for transaction API. Need to check and confirm 05-03-26: Sudarshan to check and update. 26-02-26: Journey working end to end. BTG to release for testing. 18-02-26: Patch to be shared by tomorrow. 29-01-26: Patch to be shared for raised observation. 22-01-26: Issue raised. CRM to check and share the fix. 08-01-26: Abhishek to resume UAT by tomorrow. 18-12-25: Abhishek to confirm on the Project status 11-12-25: Bank team to schedule a call for the same. 04-12-25: Awaiting update from UPI team. ETA to be shared by bank team. 20-11-25 to 27-11-25: Awaiting update from UPI team. ETA to be shared by bank team. 13-11-25: Call Setup at 4:30 for joint testing 06-11-25: Sudarshan to share for UAT testing. 30-10-25: Fixes shared. UAT Signoff to be shared by mid November. 25-09-25: Patch shared and Logs to be shared with UPI team. 04-09-25: Request to be shared with Sudarshan. 17-07-25: UAT testing in process 10-07-25: Updated Patch to be shared. 03-07-25: Revised Patch need to be shared - CRM 19-06-25: Port Opening in pending. 29-05-25: URL whitelisting still pending. 14-05-25: updated patch to be shared. 07-05-25: UAT deployment in progress 19-03-25 to 16-04-25: UAT Delivery planned for 8th May 12-03-25: PO will be shared by next week 12-02-25 to 05-03-25: FPN to be raised. 05-02-25: Proposal shared. PO Awaited 29-01-25: Awaiting UD signoff 22-01-25: UD to be shared by Friday 15-01-25: Discussion done | Krina Shah | Tejas Baban Jadhav | Akhil Kamble |  | 08-May-2025 | 361
| ISA ¦ NDML circular on usage of KRA by MFD | 118188 | HDFC DAP PO ¦ISA¦ NDML circular on usage of KRA by MFD | UAT Signedoff | CustomerNEXT | Rachael Lobo |  |  | 1 | 2 | 28-Aug-2025 | 13-11-2025 |  |  | 08-Dec-2025 | 30-Jan-2026 | 30-Nov-2025 | 06-Feb-2026 | 09-Feb-2026 |  |  | 09-Feb-2026 | 20-Apr-2026 |  |  | 04-Sep-2025 | 02-Feb-2026 | 04-Feb-2026 |  | 0 | 0 | 0 |  |  |  | 0.00 % |  |  |  | 0 | PO/IT/ACIDAES S/00234037/2025-26 |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 30-04-26: Merged patch shared. Testing in progress. Prod movement planned for 6th May tentatively. 23-04-26: UAT signed off. MTP planned for first week of May 26 16-04-26: Awaiting UAT Signoff 09-04-26: Expecting signoff by 13th April. 02-04-26: Awaiting UAT sign off. Tentative sign off by next mid-week. Prerequisites for API should be ready before prod movement 19-03-26: Journey running, Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25: Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress. | Vijayalaxmi Palav,Rachael Lobo | Yogeshwari Paike | Love Nijai,Sanket Ranbhare |  | 09-Feb-2026 | 84
| CRM : NTB NR Account Opening for Adobe / Smart App journey | 117374 | HDFC DAP PO ¦ CRM : NTB NR Account Opening | UD submitted | CustomerNEXT | Krina Shah |  |  | 1 | 12 | 24-Jul-2025 | [5 empty] | 01-Nov-2025 | 01-Nov-2025 | 01-Nov-2025 |  |  | 01-Nov-2025 |  |  |  | 05-Jun-2025 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % |  |  |  | 0 | PO/IT/ACIDAES S/00227173/2025-26 |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 16-04-26: FTS Confirmation and update from IDEA awaited. 09-04-26: FTS Confirmation Awaited. Awaiting update from IDEA. 26-02-26: FTS Confirmation will be shared by 12th March. Awaiting update from IDEA. 18-02-26: FTS Confirmation Awaited. Awaiting update from IDEA. 05-02-26: FTS technical document shared. Awaiting Update from IDEA. 29-01-26: IDEA and FTS details confirmation awaited. 22-01-26: IDEA and FTS details confirmation awaited. 08-01-26: IDEA and FTS call awaiting. 18-12-25: FTS call setup for 4:00 today 11-12-25: CRM mapping sheet to be shared by today 27-11-25: UD and API specs pending 20-11-25: Call scheduled for Monday 24th November 13-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 06-11-25: DMS API Shared. Call to be scheduled for the same and FTS KAFKA. 30-10-25: Callback to be taken up as seperate Project. Call to be setup with bank team for FTS KAFKA. 25-09-25: CallBack details Shared by Bank. Awaiting DMS Api Specs and call with FTS team 18-09-25: PO to be released by next week. 04-09-25: Updated FieldList to be shared by Krina. FTS Call to be scheduled to with tuesday. 24-07-25: UD submit. Awaiting UD sign off 17-07-25: UD to be shared 03-07-25: UD timeline to be shared by CRM 19-06-25: UD in progress 29-05-25: Flow discussion to be done with Abhishek. 14-05-25: Awaiting inputs. | Krina Shah |  |  |  | 24-Jul-2025 | 284
| Sending the KYC Flags for REKYC Dates Stamping to IDEA | 118692 | HDFC DAP PO¦ Smart ¦ KYC Flags for REKYC Dates Stamping to IDEA | Production Cutover | CRMNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 1.5 | 05-Jan-2026 | 06-01-2026 |  |  | 10-Feb-2026 | 16-Feb-2026 | 16-Mar-2026 | 16-Mar-2026 | 18-Feb-2026 |  |  | 25-Feb-2026 | 01-Apr-2026 |  | 13-Apr-2026 | 05-Jan-2026 | 17-Feb-2026 | 20-Feb-2026 |  | 0 | 0 | 0 |  |  |  | 0.00 % | 17-Dec-2025 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 16-04-26: Project gone live on 13 Apr 26 09-04-26: MTP planned for 13 Apr 26 01-04-26: UAT signed off 19-03-26: Awaiting UAT sign off. 12-03-26: SIT in progress. 26-02-26: Revised patch to be shared by tomorrow. 18-02-26: Confirmation Pending for Certificates. 29-01-26: updated dll shared by bank. CRM to check and confirm 22-01-26: Updated dll awaited. Post updated dll delivery to be shared in one week 08-01-26: UAT Delivery planned for 27th Jan, 2026. 18-12-25: UAT Delivery planned for 27th Jan, 2026. 11-12-25: PO expected by next week 04-12-25: PO expected by next week. 20-11-25 to 27-11-25: Proposal Shared. Awaiting PO 06-11-25 to 13-11-25: Awaiting UD Signoff. Tentative by Tomorrow. 30-10-25: Awaiting UD Signoff 25-09-25: UD signoff expected by Monday. 18-09-25: UD Feedback shared. 16-09-25: Updated UD sent 03-07-25 : Dll and documents to be shared by next week 29-05-25: Mohan to arrange call with vendor and other teams. 07-05-25: Feasibility in progress. 26-02-26: UAT delivery done. Deployment to be completed. 05-02-26: PO to be released by Next week Monday 29-01-26: FPN approval. PO Awaited 22-01-26: FPN approval. PO to be released by 30 JAN 08-01-26: Awaiting PO 18-12-25 : RD Received | Rachael Lobo | Satish Jadhav | Love Nijai | 20-Feb-2026 | 13-Apr-2026 | 21
| Authentication Type Stamping in AOF | 119003 | HDFC DAP PO 2026-2027 | UAT Signedoff | CRMNEXT | Umesh Ramprasad Tiwari |  |  | 1 | 0.2 | 31-Mar-2026 | 02-04-2026 |  |  | 06-Apr-2026 | 07-Apr-2026 | 15-May-2026 | 15-May-2026 | 09-Apr-2026 |  |  | 09-Apr-2026 | 29-Apr-2026 |  |  | 06-Apr-2026 | 08-Apr-2026 | 08-Apr-2026 |  | 0 | 0 | 0 |  |  |  | 0.00 % | 25-Mar-2026 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 30-04-26: UAT signed off. Tentative MTP next week 23-04-26: UAT testing in progress. Awaiting sign off. 16-04-26: UAT Delivery done, Awaiting sign off 09-04-26: UAT Delivery planned for today 02-04-26: UD sign off. 31-03-26: UD submitted. Awaiting sign off. 26-03:26: RD received. | Krina Shah |  |  |  | 09-Apr-2026 | 25
| Restriction Document Editing in CRM | 118408 | HDFC DAP PO ¦ Restricting Document Editing in CRM | UD signed off | CRMNEXT | Krina Shah |  |  | 1 | 1 | 09-Feb-2026 | 23-02-2026 |  |  |  |  | 15-Jan-2026 | 15-Jan-2026 | 15-Apr-2026 |  |  | 15-Apr-2026 |  |  |  | 03-Nov-2025 |  |  |  | 0 | 0 | 0 |  |  |  | 0.00 % | 04-Sep-2025 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Approved | 16-04-26: Proposal shared. Awaiting PO 09-04-26: Proposal shared. Awaiting PO 26-02-26: UD signed off. Proposal shared. Awaiting PO 18-02-26: Awaiting UD sign off 05-02-26: UD to be shared by 9th Feb. 29-01-26: UD to be shared by next week. 08-01-26: CRM to confirm on the feasibility. 11-12-25: CRM to confirm feasibility by 12th. 27-11-25: CRM will check feasibility and confirm by next week 20-11-25: Updated UD to be shared after feasibility check. CRM to confirm by next week 06-11-25: UD shared. 30-10-25: UD to be shared by next week Tuesday | Krina Shah |  |  |  | 09-Feb-2026 | 84
| Changes in Aadhaar e-KYC Response (PDF & XML) for Foreigners | 118273 | HDFC DAP PO¦ Digital Aadhar ¦ Changes in Aadhaar e-KYC Response | UAT | CustomerNEXT | Vijayalaxmi Palav |  |  | 1 | 0.5 | 23-Jul-2025 | 07-10-2025 |  |  | 02-Mar-2026 | 06-Mar-2026 | 15-Oct-2025 | 15-Oct-2025 | 09-Mar-2026 |  |  | 10-Mar-2026 |  |  |  | 07-Oct-2025 | 06-Mar-2026 | 09-Mar-2026 |  | 0 | 0 | 0 |  |  |  | 0.00 % | 20-Jun-2025 |  |  | 0 |  |  |  |  | #BIMG# id="cf_732" src="/app/Media/GetSmartFieldImage?x=dydabjj2mcc3rss4s7x87wv8v564amw6rmjg8mq" style="border-width:0px;width:50px;height:25px" /img> | Open | 30-04-26: No update on sign off, pending from UIDAI for correct test data . 23-04-26: No update on sign off, pending from UIDAI. 16-04-26: Issue at UIDAI for new response tag and test data. Awaiting ETA for UAT sign off. 09-04-26: Awaiting UAT sign off. Issue at UIDAI for new response tag and test data 02-04-26: Awaiting UAT sign off. Tentative: Next week 19-03-26: Awaiting UAT sign off. 12-03-26: UAT delivery done. Deployment and SIT in progress 26-02-26: PO Received. UAT delivery on 10th March. 18-02-26: PO Awaited. 05-02-26: PO Awaited. 29-01-26: PO Awaited 22-01-26: PO Awaited 08-01-26: PO Awaited 18-12-25: Awaiting UD signoff. UD to be signed off by 19th Dec. 11-12-25: Updated UD to be shared by tomorrow. 04-12-25: UD will be updated post receiving updated data from HDFC. 27-11-25: On hold till further confirmation from Mehul 30-10-25 to 20-11-25: PO Awaited 25-09-25: UD signoff to be shared tomorrow. 18-09-25: Manvi to connect with Sandeep and close UD 24-07-25: UD submitted. Awaiting sign off 03-07-25: Pending points confirmation from bank | Vijayalaxmi Palav |  |  | 09-Mar-2026 | 10-Mar-2026 | 55